DRUG POLICY ACTION PLAN OF THE CAPITAL CITY OF PRAGUE FOR THE PERIOD 2008 - 2009

Compiled by Mgr. Nina Janyšková, Drug Coordinator of the City of Prague

KOPPR

Regional Department of Drug Prevention

- Drug Policy Action Plan of the Capital City of Prague for the period 2008 - 2009

- Introduction:

The Drug Policy Action Plan of the Capital City of Prague for the period of 2008 to 2009 completes the Drug Policy Strategy of the Capital City of Prague for the period of 2008 to 2012 and is concretizing its activities.

The Drug Policy Strategy of the Capital City of Prague (further on as “the Strategy”) relays on previous strategic materials of the City, on analyses effectuated with regards to the evolution in services, coordination, and funding as well as on the drug scene. With this respect the annual reports on realization of Drug Policy for the precedent years processed by the Regional Department of the Drug Prevention were appreciated as valuable background materials.

The Strategy and the related Action Plan (further on as “the AP”) are in step with the basic conceptual materials, which are the National Drug Policy Strategy for the period 2005 to 2009 and the Action Plan for the realization of the National Drug Policy Strategy for the period of 2007 to 2009.

The individual objectives of the AP for the period 2008 - 2009 comply with the following criteria:

- objectives are real and measurable

- objectives are effective with respect to their funding and directly contribute to attain the principal objectives of the Policy

- the number of objectives in given areas is realizable

The principal objective of the Policy:

To reduce the use of all types of drugs and the potential risks and damage that can afflict individuals and society due to the drug use through the use of following strategies:

| ACTIVITIES AIMED AT PREVENTING DRUG USE OR POSTPONING FIRST EXPERIENCE OF DRUGS TO A MORE MATURE AGE. | A RANGE OF SERVICES RELATED TO ABSTINENCE THERAPY FOR DRUG USERS WHO MAKE A CONSCIOUS CHOICE TO LIVE WITHOUT DRUGS. | SERVICES TO REDUCE THE POTENTIAL HEALTH AND SOCIAL RISKS AND IMPACTS OF DRUG USE IN RELATION TO USERS NOT YET READY TO GIVE UP DRUGS, AND IN RELATION TO SOCIETY- | ACTIVITIES TO ENFORCE THE LAW IN COMBATING THE SUPPLY OF DRUGS. |
| --- | --- | --- | --- |
| Demand Reduction |  | Harm reduction | Supply Reduction |
| RESEARCH, INFORMATION, EVALUATION |  |  |  |
| INTERNATIONAL COMMITMENTS, EXPERIENCE AND COOPERATION |  |  |  |

COORDINATION

The AP was prepared for the period 2008 - 2009 and will be assessed in its time. Following an assessment of individual measures a new AP for the period of 2010 - 2011 will be prepared.

The AP is approved by the Drug Commission of the Council of the CCP and the Council itself. The plan defines the responsibilities of coordinators for the reaching of objectives. For the individual areas of the AP (education, health and social areas) are held responsible the relevant politicians, heads of divisions, departments and individual organizations.

Individual points of the AP were prepared with the contribution of the Drug Commission of the Council of the CCP (further on as “the PK RHMP”), specialized sections by the PK RHMP (further on as “Sections”) and the Regional Department of the Drug Prevention (further on as “KOPPR”).

- Technical and organizational objectives

In order to achieve the specific objectives, it is necessary to improve the quality of the current system and to create a corresponding and functional organizational setting for the implementation of the set of the Capital City of Prague (further on as “the CCP”) Drug Policy measures based on multidisciplinary cooperation. Unless these objectives attained, it would not be possible to expect any effective achievement of specific and main objectives.

1) Efficient Funding – multi-annual funding of programs constituting the basic network of services in the CCP. To continue with multi-annual funding of the programs needed on the basis of a needs analysis that would complete the service network and be based on verified scientific knowledge and also would be realized by qualified professionals.

2) Coordination at the CCP – to create enough space, in particular the personnel availability for the coordination of drug policy with respect to the volume of activities in the given action plans that would emphasize on analyses, report evaluations and the use of scientific background materials.

To improve the effectiveness of the system of primary prevention coordination in the area of education and to support it formally. Through the efforts of attaining the objectives of the program Health 21 to involve actively the divisions of the MHMP into the realization of drug measures and of other measures in the field of prevention and treatment of drug users.

3) Public Awareness – to provide objective, evidence-based information to the general public.

4) Evaluation of Activities – activities should be regularly evaluated on all levels and gained knowledge applied in practice. The Strategy will be evaluated in the relation to the AP.

- I. Primary prevention

| ### Objective | Activity | Deadline | Coordination | #### Indicator |
| --- | --- | --- | --- | --- |
| 1. Functioning and effective coordination of the specific and primary preventions with clearly delimited competences of subjects | 1.1 Coordinated support and development of programs providing specific primary prevention | Continuously | KOPPR | Number and overview of funded programs Number of program participants Amount of funds for these programs |
|  | 1.2 Regular meetings of the workgroup “Sections of the primary prevention by the PK RHMP“ | 12 x per year | KOPPR – CCP Drug Coordinator; Regional School Drug Coordinator SPJ | Plan of activities of the Section Minutes from the Section meetings Proposals of systemic solutions in the primary prevention Final reports on the Section activities Background materials for the CCP Annual Report and for the meetings of the PK RHMP |
|  | 1.3 Methodological and coordination meetings with district prevention methodologists | 4 x per year | Regional School Drug Coordinator SPJ; district prevention methodologists | Setting the program and the system of vertical cooperation within the Region’s Plan of activities of the workgroup Minutes from the workgroup meetings |
|  | 1.4 Methodological and coordination meetings with drug coordinators of the City Districts Praha 1 – 22 | 12x per year | CCP Drug Coordinator ÚMČ Praha 1 - 22 | Proposals of systemic solutions in the primary prevention Cooperation in the realization of preventive measures on local level |
|  | 1.5 Cooperation among the subjects of the MHMP dealing with the prevention – coordination, consultations and exchange of information | Continuously | KOPPR; Divisions of the MHMP | Cooperation with OSK, SKU, OKZ (criminality prevention), Ethnic minorities: - project assessments - cooperation in the preparation of strategic materials - exchange of information |

| ### Objective | Activity | Deadline | Coordination | Indicator |
| --- | --- | --- | --- | --- |
|  | 1.6 Cooperation of the Region with the central organs of the State administration: MŠMT, RV KPP, MZ, MPSV | Continuously | KOPPR; MŠMT, RV KPP, MZ, MPSV | Setting of the program and of the system of horizontal cooperation within the Region, cooperation with the RV KPP and Ministries Participation in work meetings and negotiations Participation in the subsidiary procedures for the area of specific primary prevention Presentation of the coordination system at the meeting of the Association of Regions |
|  | 1.7 Preparation of a proposal of realization, of a concept and of a method of funding of the Methodological Prevention Center | 31. 12. 2008 | KOPPR, NNO, MCSSP, Center of Addictology | Methodological coordination of workers in specific primary prevention Materials Evaluation Training |
| 2. Realization of the existent programs of the specific primary prevention | 2.1 Maintaining of the existing activities in the specific primary prevention necessary in order to secure school preventive strategies (former Minimal Preventive Programs) in the schools | Continuously | KOPPR | Number of realized programs Number of addressed children, pupils, students and pedagogues in schools Number of actions for the parents or legal representatives of children, pupils and students focused on specific primary prevention Number of functional positions of school psychologists and specialized school pedagogues including their involvement in school prevention system |
|  | ## 2.2 Coordinated support and development of the programs providing specific primary prevention | Continuously | KOPPR | Number and overview of funded programs (schools / school establishments / organizations) Number of program participants Amount of funds for these programs |

| ### Objective | Activity | Deadline | Coordination | Indicator |
| --- | --- | --- | --- | --- |
|  | 2.3 Implementation in practice of the Standards of professional aptitude for the providers of the primary prevention of use of addictive substances and of the programs of prevention of other SPJ | 31. 12. 2009 | KOPPR | Number of providers of prevention activities registered in the certification process Number of certified providers of prevention services |
|  | 2.4 Creation and utilization of the evaluation system in the programs of specific primary prevention | 31. 12. 2008 | KOPPR In collaboration with the Sections by the PK RHMP | Setting of clear criteria for the evaluation Including into the Methodological guide for submitters Including into the summary of the final report on project realization |
| 3. Available programs of targeted primary prevention and early intervention focused on the most threatened target groups | 3.1 To map and to provide support and development to organizations dealing with specific forms of the prevention of risky behavior, in particular selective and indicated preventions | 31.12. 2008 | KOPPR, Section by the PK RHMP, district prevention methodologists | Number of certified programs implementing selective and indicated primary prevention |
| 4. Securing of the professional growth of subjects entering the area of specific primary prevention | ## 4.1 Involvement of pedagogues from the Prague schools into continuous training with the objective to strengthen their competences in particular in the area of coordination of specific primary prevention at schools and in the area of general primary prevention | Start in the 1st semester of 2008, project 2008 -2009 | KOPPR, NNO, Center of Addictology, IPPP | Prepared training program Partnership with the Addictology Center - project OPPA Number of trained pedagogues Intermediary reports |
|  | 4.2 Specialized training workshops for district and school prevention methodologists of SPJ | 2 x per year | KOPPR - Regional School Drug Coordinator SPJ | Number of realized methodological and specialized activities for district and school prevention methodologists of SPJ |
|  | 4.3 Specialized training workshops for city district drug coordinators | 2 x per year | KOPPR - CCP Drug Coordinator | Number of realized methodological and specialized activities for city district drug coordinators |

| ### Objective | Activity | Deadline | Coordination | Indicator |
| --- | --- | --- | --- | --- |
|  | 4.4 Support of the training of prevention workers | Continuously | KOPPR | Number of supported projects focusing on training Number of registered students and of successful graduates |
| 5. Cooperation between the Region and services providers in the area of specific primary prevention | 5.1 Cooperation between the Region and service providers in the area of specific primary prevention | Continuously | KOPPR; NNO; A.N.O.; Section by the PK RHMP | Methodological coordination of candidates to subsidies Evaluation of the realization of projects |
|  | 5. 2 Local investigations in the establishments providing services of specific primary prevention | Continuously | KOPPR; district prevention methodologists | Visits effectuated in schools and establishments, report from the visits effectuated in the schools and establishments providing services of specific primary prevention |
|  | 5. 3 „The Methodological Center of Primary Prevention” (MCPP) - founding of a legal person - provision of a financial and organizational background | 31. 8. 2008 | KOPPR; MŠMT; CA; MČ | Strategy of the MCPP; opening of the MCPP by 1. 9. 2008 |
| 6. Provision of information to professional and lay public | 6.1 Specialized workshops and conferences for professional public | Continuously | KOPPR;NNO; CA; regions; A.N.O. | Number of professionals’ meetings |
|  | 6.2 Informing on the issue of the website of the KOPPR | Continuously | KOPPR | Website number of posted information - final and annual reports |
|  | 6.3 Updating of the database of organizations providing special services | Continuously | KOPPR | Website; printing of materials - regular update and enlargement of the offer in the area of prevention on the official website of the Region |
|  | 6.4 Meeting of the service providers in the area of specific primary prevention | 1 x per year | KOPPR; Section of the primary prevention | Prague Drug Forum – evaluation questionnaire from the meeting |

| ### Objective | Activity | Deadline | Coordination | Indicator |
| --- | --- | --- | --- | --- |
| 7. Collection of data in the area of specific primary prevention | 7.1 Organization of the collaboration in the area of unified data collection in primary prevention with the RV KPP and the MŠMT | 31.12. 2008 | KOPPR, NNO, RV KPP, MŠMT | Overview of the definition of acts in the primary prevention (PREV DATA) Output tables of data collection in the primary prevention make part of intermediary and final reports of the MHMP, RV KPP, MŠMT |
|  | 7. 2 Organization of the collaboration in the area of training and implementation of a tool for the data collection in primary prevention | 31.12. 2008 | KOPPR, RV KPP, MŠMT, NNO | Informing and providing the subjects in the Region, that implement primary prevention programs, with trainings on the use of this tool for PP data collection |
|  | 7.3 Processing of final reports on the realization of programs of primary prevention for 2007 and 2008 | February 2008 and 2009 | KOPPR | Statistic data - number of statistic outputs and information obtained in the area of primary prevention by intermediary of the software „Prevdata“ |
|  | 7.4 Annual report on the realization of drug policy in the CCP | May 2008 and 2009 |  | Annual report on the realization of the drug policy in the CCP for 2007 and 2008 |
| 8. Effective legal measures in the area of primary prevention of risk behavior | 8.1 Specification of working positions and of competences of school prevention methodologist and of district prevention methodologist in such a way that this regulation would be mandatory for the founder | 1. 9. 2009 | KOPPR, Association of Regions, MŠMT | Defined positions; Career advancement; basic CV model methodology Relationship to funds, method of financial evaluation |

- II. Treatment and After Treatment Care

| ### Objective | Activity | Deadline | Coordination | Indicator |
| --- | --- | --- | --- | --- |
| 1. Available, quality and linked network of treatment and after treatment care for users of legal and illegal drugs | ## 1.1 Maintaining quality, effectiveness and availability of existent services within their complete specter | Continuously | KOPPR; NNO | Number and overview of funded programs Number of program participants Amount of funds for these programs |
|  | ## 1.2 Mapping the availability of ambulatory care for drug users in the region and making it available on the basis of an analysis | 31.12. 2008 | KOPPR, A.N.O.; Section by the PK RHMP | Number of programs / organizations providing ambulatory care in the CCP by the standards of professional aptitude System proposal of measures for the provision of available and sufficient care |
|  | ## 1.3 Analyzing the coverage with substitution treatments (Subutex, Suboxon, Methadon, Heroin) and providing them on the basis of an analysis | 31.12. 2008 | KOPPR; A.N.O., CA; Section by the PK RHMP | Number of programs Number of clients in substitution treatments Conceptual proposal of a solution of the situation Proposal of the economic securing Proposal of a pilot program of the heroine substitution treatment |
|  | ## 1.5 Analyzing and describing the situation in provided ambulatory treatments and proposing methods and forms of ambulatory care related to the needs of clients, drug users and addicts including minorities | 2008 - 2009 | KOPPR, A.N.O., CA; Section | Definition of different forms of ambulatory care in Prague (not only strictly medical, psychiatric care); Definition and strengthening of the case management, Strengthening of protected housing – social apartments related to the treatment Strengthening of protected employment, Strengthening of family therapy, Definition of needed types and forms of ambulatory establishments |
| ### Objective | Activity | Deadline | Coordination | Indicator |
|  | ## 1.6 Coordination of treatment activities in the CCP focused on the improvement of availability and effectiveness | Continuously | KOPPR; PK RHMP (Section); NNO; A.N.O. | Number and location of treatment facilities in Prague |
|  | ## 1.7 Providing ambulatory care to specific groups – minors, mothers with children and in particular Roma and foreigners | Continuously | NNO; A.N.O. | Number and location of treatment facilities in Prague – supporting awareness Number of clients in treatments |
|  | ## 1.5 Analyzing and describing the situation in provided ambulatory care and proposing methods and forms of ambulatory treatments related to the needs of clients, drug users and addicts including minorities | 2008 - 2009 | KOPPR, A.N.O., CA; Section | Definition of different forms of ambulatory care in Prague (not only strictly medical, psychiatric care); Definition and strengthening of the case management, Strengthening of protected housing – social apartments related to the treatment Strengthening of protected employment, Strengthening of family therapy, Definition of different types and forms of ambulatory facilities |
|  | ## 1.6 Coordination of treatment activities in the CCP focused on the improvement of availability and effectiveness | Continuously | KOPPR; PK RHMP (Section); NNO; A.N.O. | Number and location of treatment facilities in Prague |
|  | ## 1.7 Provision of ambulatory care for specific groups – minors, mothers with children and in particular Roma and foreigners | Continuously | NNO; A.N.O. | Number and location of treatment facilities in Prague – providing information Number of treated clients |
| 2. Comprehensive knowledge of medical and non-medical workers on risks, prevention and after treatment care of addictions to illegal substances | ## 2.1 Provision of information on innovations and news in the system of treatment and care | 31. 12. 2008 | KOPPR; CA; IPVZ; MZ; NNO; ČLS JEP – Section LNN | Number of informative actions Number of participants |

| ### Objective | Activity | Deadline | Coordination | Indicator |
| --- | --- | --- | --- | --- |
| 3. Available and quality treatment for drug users in prisons | ## 3.1 Improvement of the cooperation between prisons and the current system of medical care | Continuously | NNO; Msp | Number of clients Retaining drugs in prisons Number of programs |
| 4. Establishment of the appropriate indication of clients for the various types of care | ## 4.1 Introduction of indication workshops in the CCP | 31. 12. 2008 | CA;NNO | Number of educative actions Number of participants |

- III. Risk Reduction

| ### Objective | Activity | Deadline | Coordination | Indicator |
| --- | --- | --- | --- | --- |
| 1. Available, quality and linked network of the Harm Reduction for users of legal and illegal drugs | ## 1.1 Maintaining quality, effectiveness and availability of existent services within their complete specter | Continuously | KOPPR; NNO | Number and overview of subsidized programs Number of program participants Amount of funds for these programs |
|  | ## 1.2 Mapping the availability of field programs in the individual districts of the CCP respecting the condition of effectiveness of the given service by intermediary of the coordination of existent activities | Continuously | KOPPR; NNO; PK MČ | Analysis of availability and of needs, in particular at the City suburbs Support of the programs |
|  | ## 1.3 Mapping the situation in the area of Harm Reduction services on the basis of unified data in the individual indicators | 30. 5. 2008 30. 5. 2009 | KOPPR; A.N.O.; PK RHMP (Section) | Report on the evolution at the drug scene Number of clients Exchange program Number of workers in the services Costs |
|  | ## 1.4 Mapping actually working AT ordinations, assessment of situation and availability | 31.12. 2008 | KOPPR; ČSL JEP | Report on the present situation Number of the AT ambulances in Prague providing real services not only to alco-clients Number of clients in these institutions |
|  | ## 1. 5 Support of the Harm Reduction program with an accent on HIV prevention | Continuously | KOPPR; NNO | Adult education actions Tests Mapping the drug scene Provision of protection aids |

| ### Objective | Activity | Deadline | Coordination | Indicator |
| --- | --- | --- | --- | --- |
| 2. Reduction of injection drug users | ## 2.1 Strengthening of low threshold facilities and of field programs | Continuously | HMP; RV KPP; KOPPR | Concept of the method and forms of solution of the situation Enlargement and strengthening of personnel and financial aspects of the existent programs Alternatively a solution proposal – realization of new TP and NZ programs |
|  | ## 2.2 Material of the best practice “Safely in the night-life” | 31. 12. 2008 | KOPPR | Providing translation and distribution |
| 3. Reduction of risks related to the use of cannabis substances, synthetic drugs used at the dance scene, dissolvents and alcohol, and related to other addictive behaviors | ## 3.1 Field programs focused to the hidden drug scene and to the drug use at dance parties | Continuously | KOPPR; NNO | Number of programs focused on apartments and the dance scene Number of clients |
| 4. Reduction of risks in the specific groups of drug users (e.g. in ethnic minorities, drug users in prisons etc.) | ## 4.1 Support and strengthening of projects dealing with the issues of minorities and persons threatened with social exclusion | Continuously | KOPPR, A.N.O.; A.N.O., NMS; PK RHMP (Section) | Cooperation with research institutions and projects – results – description of the situation in the CCP Number of persons and of acts for these target groups Report on the situation in these target groups Financial support of projects with this orientation |

- IV. Reduction of Supply and Law Enforcement – coordinated by the repression units

| ### Objective | Activity | Deadline | Coordination | Indicator |
| --- | --- | --- | --- | --- |
| 1. Training of workers of the MPHMP and the Police of the CR in the area of prevention of drug addictions | ## 1.1 Professional training on the issues of drug prevention – joining the basic theoretic knowledge with the practice | Continuously | KOPPR and the prevention unit in the MP HMP and the PČR | Number of workshops Number of participants |

- V. Information – research - evaluation

| ### Objective | Activity | Deadline | Coordination | Indicator |
| --- | --- | --- | --- | --- |
| 1. Information | ## 1.1 Informing on the issue of the Internet KOPPR website | Continuously | KOPPR | Website - number of posted information - final and annual reports |
|  | ## 1.2 Update of the database of organizations offering special services | Continuously | KOPPR | Website; - regular update and enlargement of the offer in the area of prevention on the official website of the Region |
|  | ## 1.3 Securing the availability of information in printed form | Continuously | KOPPR; NNO | Printing of information materials |
|  | ## 1.4 Organization of and co-participation in professional workshops and conferences | Continuously | KOPPR; NNO | Number of actions Number of participants Recording |
|  | ## 1.5 Organization of long-term training professional workshops for the drug commissions of the city districts and for district prevention methodologists | 2 x per year | KOPPR | Number of actions Number of participants Minutes |
| 2. Collection and analysis of data on the drug situation in the CCP | ## 2.1 Securing the coordination of data collection between the RV KPP and the NMS | 30. 5. 2008 | KOPPR, RV KPP, NMS, A.N.O. | Unified tool for data collection Unified tables for the PZ and ZZ at the MHMP and the RV KPP |
| ### Objective | Activity | Deadline | Coordination | Indicator |
|  | ## 2.2 Specification for the elaboration of the analysis “Minimal network of services in the CCP able to be covered with funds“ | 30. 5. 2008 | KOPPR; PK RHMP | Definition of the minimal network of services |
|  | ## 2.3 Analysis of the target group of Prague low-threshold programs | 30. 5. 2008 | KOPPR ; NNO | Number of clients in the programs Sufficiency of the services - number of workers - availability - funds |
|  | ## 2.4 Analysis of the services of substitution programs and of the need for their expansion | 30. 5. 2008 | KOPPR ; NNO | Number of clients in the programs Sufficiency of the services - number of workers - availability - funds |
| 3. Evaluation of the CCP Drug Policy | ## 3.1 Annual report on the realization of the CCP Policy | 1x per year 2008 a 2009 | KOPPR; Section by the PK RHMP; PK MČ | Comprehensive mapping of the realization of the CCP Drug Policy for the last year |
|  | ## 3.2 Prague Drug Forum I. | 1x per year 2008 a 2009 | KOPPR; Section by the PK RHMP; PK MČ | Evaluation of the programs of specific primary prevention Exchange of information |
|  | ## 3.3 Prague Drug Forum II. | 1x per year 2008 a 2009 | KOPPR; Section by the PK RHMP; PK MČ | Evaluation of the programs of Harm Reduction Exchange of information |
|  | ## 3.4 Prague Drug Forum III. | 1x per year 2008 a 2009 | KOPPR; Section by the PK RHMP; PK MČ | Evaluation of the programs of – treatment, after treatment care, substitution Exchange of information |
|  | ## 3.5 Evaluation of the final reports | 1x per year 2008 a 2009 | KOPPR; Section by the PK RHMP; | Evaluation of the final reports on the realization of Prague programs supported from the City budget or the State Budget in the last year |
| ### Objective | Activity | Deadline | Coordination | Indicator |
|  | ## 3.6 Drug Commission of the CCP Council | 12 x per year | PK RHMP | Evaluation of the situation at the drug scene and proposals of a solution for the Council of the CCP Evaluation of the projects |
|  | ## 3.7 Local investigation in the organizations providing services of specific prevention | Continuously | KOPPR | Visits in organizations - minutes from the visits |
|  | ## 3.8 Controls effectuated by the Division of financial control of the MHMP | Continuously | KOPPR; OFK MHMP | Outputs from the controls |

- VI. Coordination and Funding

| ### Objective | Activity | Deadline | Coordination | Indicator |
| --- | --- | --- | --- | --- |
| 1. Functional legal and organizational framework of the present CCP Drug Policy | ## 1.1 Securing the drug policy tools | Continuously | MHMP; RV KPP; Ministries | Conceptual materials Evaluation Multidisciplinary cooperation |
|  | ## 1.2 Act on Social Services | 30. 5. 2008 | KOPPR | Cooperation at the preparation of the Community Plan Projects of drug services in social programs Integration of inspection demands into the certifications |
| 2. Effective and quality coordination of the drug policy in the CCP | ## 2.1 Personnel strengthening of the KOPPR | 30. 6. 2008 | PK HMP; MHMP | Personnel provision of modalities of the services, i.e. Specific primary prevention – 1,0 full-time Other types of prevention – 1,0 full-time CCP Drug Policy, interdisciplinary cooperation, IVH – 1,0 full-time Total – 3,0 full-times |
| ### Objective | Activity | Deadline | Coordination | Indicator |
| 3. Coordination of the drug policy on the territory of the CCP | ## 3.1 Coordination of activities of the City Districts Praha 1 – 22 | Continuously | KOPPR, City District Drug Coordinators Praha 1 – 22 | Active cooperation: - participation to meetings - participation to specialized workshops and conferences - unification of conceptual materials - mutual provision of information on programs realized in the City District - evaluation of projects |
|  | ## 3.2 Coordination of activities in the area of SPJ prevention | Continuously | KOPPR; district prevention methodologists | Active cooperation: - participation to meetings - participation to specialized workshops and conferences - unification of conceptual materials - mutual provision of information on programs realized in the City District - evaluation of the projects |
|  | ## 3.3 Coordination of activities of the MHMP units dealing with the prevention | Continuously | KOPPR; divisions of the MHMP | Cooperation with the OSK, SKU, OKZ (Criminality Prevention), Ethnic Minorities: - evaluation of the project - cooperation on the conception of strategic materials - Exchange of information |

| ### Objective | Activity | Deadline | Coordination | Indicator |
| --- | --- | --- | --- | --- |
|  | ## 3.4 Coordination of activities on the national level | Continuously | KOPPR | Active cooperation: - participation to meetings - participation to specialized workshops and conferences - Exchange of information - RV KPP; Ministries; Regional PK and prevention coordinators - active participation of a representative of the City at the meetings of Committees of the RV KPP |
|  | ## 3. 5 Coordination of programs of the organizations providing drug prevention services | Continuously | KOPPR; PK RHMP | Mapping the situation and solution proposals Setting priorities for tenders |
| 4. Funding Granting of subsidies to quality and effective programs of drug policy | ## 4.1 To coordinate the forms of applications for funds in the CCP drug policy projects with the applications in the RV KPP | 30.6. 2008 | KOPPR, A.N.O., RV KPP | Unified forms of applications, intermediary and final reports by the type of services, compatible Internet applications |
|  | ## 4.2 Organization of the tenders for funding of services for the next year | 2008 2009 | KOPPR; PK RHMP | Tenders for „Healthy City of Prague 2009“ and „ Healthy City of Prague 2010“ Tenders of the RV KPP and the Ministries |
|  | ## 4.3 Innovation of the system of drug policy funding ## Definition of the procurement system for services, tariff of acts in the addictology area, processing of a cost benefit analysis | 2008 – 2009 | KOPPR, A.N.O., (foreign subject - VNN Nederland), Center of Addictology | Definition of acts and their prices Costs of addictology programs for 2000 – 2007 Tariff of services |

- VII. International Cooperation

| ### Objective | Activity | Deadline | Coordination | Indicator |
| --- | --- | --- | --- | --- |
| 1. More pronounced cooperation of the CCP with international organizations and institutions in the area of drug policy | ## 1.1 Organization and realization of international conferences in the area of addictology | 2008 - 2009 | KOPPR, A.N.O; CA | Number of actions Number of participants |
| 2. Raising the level of training and information in the area of international drug legislation, cooperation and activities | ## 2.1 Linking to the system of early warning | 2009 | KOPPR, NMS | Interconnection with the NMS and EMCDDA systems, entry possible only for organization workers on different levels ……. |
|  | ## 2.2 Organization of early warning information in the area of international legislation, cooperation and activities | 2009 | KOPPR, RV KPP, NMS | Web links to the news - on the websites of the NMS and of the RV KPP - the CCP – mail conference |
| 3. Strengthening of cooperation between governmental and non-governmental organizations in the area of international cooperation | ## 3.1 Training of workers of the heroine substitution center in Zurich in Prague substitution centers and other establishments | 2008 | NNO; A.N.O. | Exchange of information Number of traineeships Number of participants |
|  | ## 3.2 Organization of mutual traineeships in EU countries for professionals from the area of addictive diseases | 2008 2009 | NNO; A.N.O.; ČSL JEP | Number of traineeships Number of participants |
| 4. More pronounced cooperation of the CCP with international organizations and institutions in the area of drug policy | ## 4.1 Continuation of the cooperation within the framework of the project Democracy, Drugs and pilot Cities, focused on the local community and the local policy | 2008 2009 | KOPPR; NNO; A.N.O. | Exchange of information Number of visits Number of participants |